## Slide 1: Standard for Infrastructure Procurement and Delivery Management ( SIPDM)
Mossel Bay Municipality
Presented by Duane Scholtz

## Slide 2: Content
Background and Purpose
Standard for Infrastructure Procurement and Delivery Management
Gateway Concept
End-Of Stage Deliverables
Gateway review
Framework Contracts
Key considerations of SIPDM policy of Municipalities
Explore Endless Horizons

## Slide 4: Background and Purpose
First circular was issued in October 2015 (Circular 77)
The purpose of the Circular is to provide guidance to municipalities and municipal entities to establish a suitable supply chain management system for infrastructure delivery which is better able to deliver value for money, while minimizing the scope of corruption.

## Slide 5: Background and Purpose

## Slide 6: Standard for Infrastructure Procurement and Delivery Management - Coverage
Infrastructure:
Immovable assets which are acquired, constructed or which results from construction operations; or
Moveable assets which cannot function independently from purpose built immovable assets
This standard prescribes:
A control framework for the planning, design and execution of infrastructure projects, the tracking of such projects and the monitoring of performance
A control framework for infrastructure procurement
Requirements for the following matters ass applied to infrastructure procurement and delivery management:
  Institutional arrangements
  Demand management
  Acquisition management
  Logistics management
  Disposal management
  Reporting of supply chain management information
  Regular assessment of the supply chain management performance and
  Risk management and internal control

## Slide 7: Standard for Infrastructure Procurement and Delivery Management – Coverage cont.
Standard does not apply to:
The storage of goods and equipment following their delivery to an organ of state which are stored and issued to contractors or to employees of the organ of state
The disposal or letting of land
The conclusion of any form of land availability agreement
The leasing or rental of moveable assets
Public private partnerships and
The provision of municipal services by means of external mechanisms referred to in Chapter 8 of the Municipal Systems Act.

## Slide 8: Gateway Concept

## Slide 9: Control framework for planning, design and execution of infrastructure projects
Stages 3 to 9 may be omitted where the required work does not involve the provision of new infrastructure or the rehabilitation, refurbishment or alteration of existing infrastructure.
Stages 5 and 6 may be omitted if sufficient information to proceed to stage 7 is contained in the stage 4 deliverables.
A stage shall only be complete when the deliverables has been approved or accepted by the person designated in the policy.
Prefeasibility and feasibility reports shall be required as end-of stage deliverables for stage 3 and 4, respectively, where one or more of the following applies:
  A major public enterprise where the total project capital expenditure exceeds R1,5 billion; or
  An organ of state subject to the Public Finance Management Act other than a major public enterprise where the total project capital expenditure exceeds R1 billion including VAT, or where expenditure per year for a minimum of three years exceeds R250 million per annum including VAT.
  The organ of state’s infrastructure procurement and delivery supply chain management policy requires that prefeasibility and feasibility reports be produces during stages 3 and 4 respectively. (7.5 Billion)

## Slide 10: END OF STAGE DELIVERABLES

## Slide 11: Control framework for planning, design and execution of infrastructure projects

## Slide 12: Control framework for planning, design and execution of infrastructure projects

## Slide 13: Control framework for planning, design and execution of infrastructure projects

## Slide 14: Gateway review

## Slide 15: FRAMEWORK CONTRACTS
The Essence of a Framework Contract
A Framework Contract is designed to enable employers to invite tenders from contractors for the supply of goods, construction works or services to be provided on an ‘as required’ basis:
Over a set contract term ( from 2 to 5 years, usually 3 for construction);
By appointment of ONE OR MORE contractors (called Suppliers) under the framework;
Within a broadly defined scope of work for the Framework as a whole BUT WHICH IS NOT QUANTIFIED at tender stage, and
Without guaranteeing any quantum of goods, works or services.

## Slide 16: FRAMEWORK CONTRACTS
The Advantages of a Framework Contract
Once in place, FC’s can reduce the turnaround time of tender procurement.
FC’s provide a stable environment and supply of contractors (Suppliers) available to execute works over the contract term.

## Slide 17: FRAMEWORK CONTRACTS
Framework Contract are limited by:
The scope of work envisaged by Framework;
The geographical region in which the Framework opeates;
The contractors’ grading and monetary value of work envisaged.
IMPORTANT:
FC”s are not set to make the current system of general open bidding redundant

## Slide 18: FRAMEWORK CONTRACTS
How a framework contract is implemented
A Framework Contract:
Is secured by means of OPEN COMPETITIVE BIDDING like any other tender;
Comes in the form of a tender document;
Enables procurement over a set contract term of ONE or MORE contractors (Framework Suppliers) who can be called to perform construction works or services;
Enables the Employer to request delivery construction works and services in the form of WORK PACKAGES to selected appointed suppliers in the Framework without having to go to the open market (tender) every time works is required which is covered by scope of framework;
Uses the rates and prices provided by tenderers at this Framework tender stage as the quotation information upon which all quotes for work packages will be based during the set contract term.

## Slide 19: FRAMEWORK CONTRACTS
How a framework contract is implemented (continued)
A Framework Contract:
Is generally for experiences and skilled contractors and not suited for engagement with startup contractors;
Usually does not cater for contractors with a CIDB grading below 3;
Is managed through regular meetings ((Framework Core Management Group) between Employer and Framework Suppliers;
Is managed ‘openly’ i.e with complete transparency as to who gets what , and how much.

## Slide 20: Procurement activities and gates associated with the issuing of an order in terms of a framework agreement

## Slide 21: FRAMEWORK CONTRACTS ALIGNED WITH SIPDM

## Slide 22: FRAMEWORK CONTRACTS ALIGNED WITH SIPDM

## Slide 23: Key considerations to SIPDM policy of Municipalities
  Implementation of the Standard for Infrastructure Procurement and Delivery Management
Infrastructure procurement and delivery management shall be undertaken in accordance with the all applicable legislation and the relevant requirements of the latest edition of the National Treasury Standard for Infrastructure Procurement and Delivery Management.
Pre-feasibility and feasibility reports are required on all infrastructure procurement from R50 million. - Vary for each Municipality
Stage 3 to 7 are required for infrastructure procurement from R50 million – Vary for each Municipality
Mayor Capital Project threshold should be determined per Municipality.
Each Municipality should determine their implementation threshold and implementation date.
Should be at least 4% of the total Assets as per Annual financial statement

## Slide 24: Assignment of responsibilities for approving or accepting end of stage deliverables.

## Slide 26
Activity |  | Sub-Activity (see Table 3 of the standard) |  | Key action | Person assigned responsibility to perform key action
1* | Establish what is to be procured | 1.3 PG1 | Obtain permission to start with the procurement process | Make a decision to proceed / not to proceed with the procurement based on the broad scope of work and the financial estimates. | Director or delegate
2* | Decide on procurement strategy | 2.5 PG2 | Obtain approval for procurement strategies that are to be adopted including specific approvals to approach a confined market or the use of the negotiation procedure | Confirm selection of strategies so that tender offers can be solicited | Director or delegate
3 | Solicit tender offers | 3.2 PG3 | Obtain approval for procurement documents | Grant approval for the issuing of the procurement documents | Bid Specification Committee
 |  | 3.3 PG4 | Confirm that budgets are in place | Confirm that finance is available for the procurement to take place | Director or delegate
4 | Evaluate tender offers | 4.2 PG5 | Obtain authorisation to proceed with next phase of tender process in the qualified, proposal or competitive negotiations procedure | Review evaluation report, ratify recommendations and authorise progression to the next stage of the tender process | Bid Evaluation Committee
 |  | 4.7 PG6 | Confirm recommendations contained in the tender evaluation report | Review recommendations of the Bid Evaluation Committee and refer back to Bid Evaluation Committee for reconsideration or make recommendation for award | Bid Adjudication Committee
5 | Award contract | 5.3 PG7 | Award contract | Formally accept the tender offer in writing and issue the contractor with a signed copy of the contract | Director or delegate
 |  | 5.5 GF1 | Upload data in financial management and payment system | Verify data and upload contractor’s particulars and data associated with the contract or order | Director or delegate
 |  | 6.4 PG8A | Obtain approval to waive penalties or low performance damages. | Approve waiver of penalties or low performance damages | Director or delegate
 |  | 6.5 PG8B | Obtain approval to notify and refer a dispute to an adjudicator | Grant permission for the referral of a dispute to an adjudicator or for final settlement to an arbitrator or court of law | Director or delegate
6 | Administer contracts and confirm compliance requirements | 6.6 PG8C | Obtain approval to increase the total of prices, excluding contingencies and price adjustment for inflation, or the time for completion at the award of a contract or the issuing of an order up to a specified percentage21 | Approve amount of time and cost overruns up to the threshold | Director or delegate Above R200 000 Bid Adjudication Committee
 |  | 6.7 PG8D | Obtain approval to exceed the total of prices, excluding contingencies and price adjustment for inflation, or the time for completion at award of a contract or the issuing of an order by more than 20% | Approve amount of time and cost overruns above the threshold | Municipal Manager Inform Council of increase above the threshold
 |  | 6.8 PG8E | Obtain approval to cancel or terminate a contract | Approve amount | Director or delegate
 |  | 6.9 PG8F | Obtain approval to amend a contract | Approve proposed amendment to contract | Director or delegate

## Slide 27: Questions?

## Slide 28: Thank you